## Tasking list
Check Required Task |  | Phase/Task
| 1 | Pre-Design Services Phase
| 1A | Data Collection and programming for the project.
| 1A1 | Project coordination meetings with local agencies and owner representatives.
| 1A2 | Review and Present to Stakeholders.
| 1A3 | Preform neighborhood and community charettes as required.
| 1A4 | Prepare a scope design concept or preliminary design report
| 1B | Site Analysis Services
| 1B1 | Collecting site data - boundry surveying
| 1B2 | Collecting site data - topographical surveying
| 1B3 | Site studies - environmental
| 1B4 | Site studies - Traffic
| 1C | Preparation of site plans.
| 1D | Meeting with public utilities
| 1E | Permitting applications (approvals and presentations)
| 1F | All other services as identified by the City Project Manager. See added sheet for additional services under Phase 1.
| 2 | Preliminary Design/Development (Estimated 30%) Phase
| 2A | Research the project and make recommendations to the City throughout this phase. City will provide the Project description.
| 2A1 | Prepare a conceptual design and cost estimate.
| 2A2 | Attend all public hearings and public meetings related to the project.
| 2A3 | Conduct necessary field reviews.
| 2A4 | Confer with the sponsor on project require­ments, programming, finances, schedules, early phases of the project, and other pertinent matters; meet with the concerned agencies and parties on matters affecting the project.
| 2A5 | Collect data and undertake field investigations; geological engineering and surveys; and architectural, engineering, land surveys, and environmental stud­ies.
| 2A6 | Plan, procure, and/or prepare necessary surveys, geological engineering investigations, field investigations, and architectural and engineering studies required for preliminary design considerations.
| 2A7 | Develop design schematics, studies, sketches, and exhibits, lists of environmental and aesthetic considerations, project recommendations, preliminary layouts, and updated cost estimates.
| 2A8 | Assist the City in the preparation of all neces­sary and required documents for State and federal grants, includ­ing Disadvantaged Business Enterprise (DBE) plan and goals, and exhibits.
| 2A9 | Develop source documentation related to the design of the project.
| 2A10 | Submit final preliminary phase documents and recommendations to City for review and approval prior to finalization by the Consultants.
| 2A11 | Meet with Purchasing Division to review consultant checklist and requirements.
| 2A12 | All other services as identified by the City Project Manager. See added sheet for additional services under Phase 2
| 3 | Intermediate Design (60-90%) Phase
| 3A | Refinement of schematics design with staff and advisory personnel. Scaled floor plans and elevations of the interior space utilizations by occupants, selections of building system. Discussion of cost effective and functional methods to promote the use of green materials through innovative architectural processes. Strive to meet LEED standards and Energy Star optimum rating standards whenever cost effective.
| 3B | Schedule and attend meetings and design conferences to obtain informa­tion and to coordinate or resolve design matters.
| 3C | Prepare necessary reports and recommendations.
| 3D | Ensure red, green, and brown colored marked up plans and utility relocation schedules to all agencies are prepared and submitted as required.
| 3E | Prepare plans, specifications, and cost estimates as appropriate for 60% and 90% level of completion. Conduct a detailed value engineering analysis, if applicable and if requested. Print, bind as necessary, and provide all necessary copies of engineering drawings and contract specifications.
| 3F | All other services as identified by the City Project Manager. See added sheet for additional services under Phase 3.
| 4 | Final Design (100%) Phase
| 4A | Ensure red, green, and brown colored marked up plans and utility relocation schedules to all agencies are prepared and submitted as required.
| 4B | Submit Permit Applications to and respond to all subsequent Requests for Additional Information from State, Federal, and Local reviewing agencies, as appropriate.
| 4C | Conduct necessary field reviews.
| 4D | Attend public hearings and public meetings related to the project.
| 4E | Provide all necessary land surveys and legal descriptions for right-of-way and easement acquisitions.
| 4F | Prepare final construction plans, specifications and bid form and submit to City Staff for review and approval prior to finalization.
| 4G | Preparation of final working drawings and specifications.
| 4H | All other approvals as necessary to complete the project
| 4I | All other services as identified by the City Project Manager. See added sheet for additional services under Phase 4.
| 5 | Bidding and negotiations Phase
| 5A | Provide the City specified number of plan sets, specifications, and the scope of work for this phase.
| 5B | Assist the Purchasing Division with the preparation of all bid documents as requested.
| 5C | Ensure that all bid document meet the Consultant Checklist provided by the Purchasing Division. Copy of the current Consultant Checklist is in Appendix A.
| 5D | Be present at all pre-bid meetings.
| 5E | Provides answers to question from the pre-bid meeting and addenda as requested
| 5F | Be present at the bid opening at the discretion of the City.
| 5G | Analyze bid results and provide a calculated and verified bid tab in a formatted as specified by the City.
| 5H | Verify references and contactors qualification for the selected project.
| 5I | Furnish recommendations on the award in writing.
| 5J | Provide assistance to the City with negotiations, as required.
| 5K | Prepare a complete set of conformed plans and specifications to include all changes made through addenda.
| 5L | All other services as identified by the City Project Manager. See added sheet for additional services under Phase 5
| 6 | Constructions Phase
| 6A | Conduct a post bid/pre-construction conference and provide meeting minutes to the City for its review and approval prior to distribution unless otherwise directed by the City. The City may chose to record the minutes.
| 6B | Review and forward for City approval all submittals for the project.
| 6C | Provide construction staking of the project by a Florida licensed Land Surveyor.
| 6D | Provide construction inspection of the project by a fully qualified individual with experience in the specialty as required by the City and as approved by the City on one of the following basis:
| 6D1 | A full time basis by at least one (1) individual. Full time shall be described such that the inspector will be present on the site between 87% and 100% of the time that the contractor is productively working.
| 6D2 | A part time basis by at least one (1) individual. Part time shall be described such that the inspector will be present on the site between 14% and 86% of the time that the contractor is productively working.
| 6D3 | An occasional basis by at least one (1) individual. Occasional shall be described such that the inspector will be present on the site between 3% and 13% of the time that the contractor is productively working.
| 6E | Provide quality control (testing) services utilizing a qualified testing laboratory located in the State of Florida as approved by the City.
| 6F | Conduct regularly scheduled project status meetings on a schedule determined by the City and provide meeting minutes to the City for its review and approval prior to distribution.
| 6G | Review and recommend approval to the City, the contractor’s quantities and pay requests.
| 6G1 | Furnish record drawings with no disclaimers, unless authorized by the City, based on the contractor’s redlined construction plans and surveys conducted by a Florida licensed Land Surveyor. Such record drawings shall be provided in both hard copy and electronic media acceptable to the City.
| 6H | Construction Observation
| 6H1 | Consultant shall observe the construction and ascertain to the best of the consultant’s ability that the project is constructed in accordance with approved plans and specifications.
| 6I | All other services as identified by the City Project Manager. See added sheet for additional services under Phase 6.

## sup task list
Page _____________ of ____________
Corresponding Task Item | Description of Additional Task
Add additional task from the Master list corresponding item number.